## PROJECT PROFILE
Defect Tracking Sheet
TMT/TD05/TMP
Project ID | Make My Journey_002
Project Name | Make My Journey User Registration Form
Prepared/Modified by | Role | Date of Preparation
Vandanapu Bhavya | Tester | 2018-06-27
Reviewed by | Role | Date of Review
name
Approved by | Role | Date of Approval
name | Test Manager
Circulation List
Version Number | 2

## DEFECT TRACKING SHEET
Project ID: Online Banking System(OBS) |  | Project Name : Online Banking Form
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Fixed By | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments
OBS_001 | password | When invalid user id and password is entered more than 3 times the account doesn't get locked. | Detailed Description: The invalid username and password are entered more than 3 times Steps to reproduce a bug: 1. Open Browser 2. Enter URL for the website 3. Enter the admin details 4. Enter the invalid username and password more than 3 times. 5. Click on Login button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the account is not blocked when invalid details are given more than 3 times. | Coding | Internet Explorer | Internal Dev | Medium | High | 1.1 | Build 1.0 | 2018-07-19 | bhavya |  | ACT | Test Cycle 1 | TC_AdminPass_06
OBS_002 | Add New Account | The Account Holder Registration page is not able to navigate for adding new account. | Detailed Description: The Account holder registration page is not able to navigate Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on admin details 4. Enter the Valid credentials 5. Click on Login button 6.The website should generate Account Holder Registration page. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the Account Holder Registration page is not generated. | Coding | Internet Explorer | Internal Dev | High | High | 1.1 | Build 1.0 | 2018-07-19 | bhavya |  |  | Test Cycle 1 | TC_AddAc_01
OBS_003 | Acc_Hold_Name | The account holder name in the registration page ia accepting numerical characters | Detailed Description: The holder name in the registration form is accepting numerical characters Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on admin details 4. Enter the Valid credentials 5. Click on Login button 6.The website should generate Account Holder Registration page. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the account holder name is accepting numerical characters. | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2018-07-19 | bhavya |  |  | Test Cycle 1 | TC_AcHName_03
OBS_005 | Register | The account holder is unable to register by clicking register button even if fields are filled | Detailed Description: The holder is able to register if fileds are not entered Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on admin details 4. Enter the Valid credentials 5. Click on Login button 6.The website should generate Account Holder Registration page. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the account holder is able to register if fileds are not entered properly | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2018-07-19 | bhavya |  |  | Test Cycle 1 | TC_Reg_02
OBS_006 | Reset | The account holder is not able to reset by clicking reset button | Detailed Description: The holder is not able to reset the reset button Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on admin details 4. Enter the Valid credentials 5. Click on Login button 6.The website should generate Account Holder Registration page. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the account holder is not able to reset the fields | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2018-07-19 | bhavya |  |  | Test Cycle 1 | TC_Res_02
OBS_007 | view_monthly_transactions | The account holder is not able to scroll the select month bar to select the month | Detailed Description: The holder is not able to select the month in select bar Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on admin details 4. Enter the Valid credentials 5. Click on Login button 6.The website should generate Account Holder Registration page. 7.The website should generate View transaction Reports. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the account holder is not able to select the month in scroll bar. | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2018-07-19 | bhavya |  |  | Test Cycle 1 | TC_MT_02
OBS_008 | view_transactions | The account holder is not able to view the transactions by click view transactions between given duration | Detailed Description: The holder is not able to view the transactions Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on admin details 4. Enter the Valid credentials 5. Click on Login button 6.The website should generate Account Holder Registration page. 7.The website should generate View transaction Reports. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the account holder is not able to view the transaction by clicking that button. | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2018-07-19 | bhavya |  |  | Test Cycle 1 | TC_VT_02
OBS_009 | multiple_accounts | The Mini/Detailed statements are not present in account holder page | Detailed Description: The holder is not able to view mini/detailed statements Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on admin details 4. Enter the Valid credentials 5. Click on Login button 6.The website should generate Account Holder Registration page. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the account holder is not able to view the mini/detailed accounts(multiple accounts) they are not present in account holder page. | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2018-07-19 | bhavya |  |  | Test Cycle 1
OBS_010 | request_change | The request for change in communication address/mobile number for bank account is not present | Detailed Description: The holder is not able to change mobile number/address Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on admin details 4. Enter the Valid credentials 5. Click on Login button 6.The website should generate Account Holder Registration page. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the account holder is not able to change in communication address/mobile number in account holder page. | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2018-07-19 | bhavya |  |  | Test Cycle 1
OBS_011 | fund_transfer | The fund transfer for bank accounts by clicking 'Add a payee' button is not provided in page | Detailed Description: The holder is not able to transfer funds into bank accounts Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on admin details 4. Enter the Valid credentials 5. Click on Login button 6.The website should generate Account Holder Registration page. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the account holder is not able to transfer the funds into another account. | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2018-07-19 | bhavya |  |  | Test Cycle 1
OBS_012 | payments | The transactions is not completed successfully if pay button is not provided in page | Detailed Description: The holder is not able to complete transactions successfully Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on admin details 4. Enter the Valid credentials 5. Click on Login button 6.The website should generate Account Holder Registration page. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the account holder is not able to do transactions successfully if pay button is not provided | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2018-07-19 | bhavya |  |  | Test Cycle 1
OBS_013 | pan_card | The registration page is showning the pan card is already existing for every new account | Detailed Description: The holder page is showing the pan card is already existing Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on admin details 4. Enter the Valid credentials 5. Click on Login button 6.The website should generate Account Holder Registration page. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the account holder page is showing the pan card is already existing. | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2018-07-19 | bhavya |  |  | Test Cycle 1 | Tc_Pc_07
OBS_014 | Email_Id | The registration page is showning the Email Id is already existing for every new account | Detailed Description: The holder page is showing the Email Id is already existing Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on admin details 4. Enter the Valid credentials 5. Click on Login button 6.The website should generate Account Holder Registration page. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the account holder page is showing the Email Id is already existing. | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2018-07-19 | bhavya |  |  | Test Cycle 1 | Tc_Eml_03
OBS_015 | pan_card | The pan card is validating when it left with blank | Detailed Description: The holder page is showing the pan card is left with blank is also validating Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on admin details 4. Enter the Valid credentials 5. Click on Login button 6.The website should generate Account Holder Registration page. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the account holder page is showing the pan card is validating when left with blank. | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2018-07-19 | bhavya |  |  | Test Cycle 1 | Tc_Pc_06
Note on A3: Give a unique number for the Defect Id
Note on B3: Give the name of the module being tested
Note on C3: Summarize the defect in 1 or 2 lines
Note on D3: A detailed description of the defect
Note on E3: Categorize the defect into the one of the values given in the drop down list
Note on F3: Mention the name of the browser the defect was found in.
Note on G3: Mention the environment in which the defect was found.
Note on H3: P0 defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption P1 defect is a defect wherein a function does not work and a tedious work around exists. e.g. One of menu options does not work. P2 defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. P3 defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling. “High” severity defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption, some of the menu functions do not work “Medium” severity defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. “Low” severity defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling.
Note on I3: Prioritize the defect
Note on J3: Enter the Release # in which the defect was detected.
Note on K3: Enter the Build # in which the defect was detected.
Note on L3: Mention the date the defect was reported
Note on M3: Name of the person who reported the defect.
Note on N3: Name of the person the defect is assigned to.
Note on O3: Can have values: VERIFIED CLOSED FIXED ACT-Active CNR-Could Not be Reproduced NOD- Reported Bug Not a Defect REP- Repeated
Note on P3: Values can be: PPR-Peer to Peer Review PR-Peer Review SR-Self/Programmer Review QPR-10% Quality Probe(Review) RT-Random Testing UTC-Using Test Cases
Note on Q3: Mention the Test Case No that the defect was found while testing
Note on R3: Name of the person who fixed the defect.
Note on S3: Mention the date the defect was Fixed
Note on T3: Mention the date the defect was verified
Note on U3: Name of the person who will be verifying whether the defect has got fixed after the defect has being worked upon
Note on V3: Enter the Release # in which the defect was available for verification
Note on W3: Enter the Build # in which the defect was available for verification
Note on X3: Attach the proofs showing the defect-screenshots,temp files,etc
Note on Y3: Should include all the comments on the defects till date by all touching the defect.It should be captured date wise.