## PROJECT PROFILE
Defect Tracking Sheet
TMT/TD05/TMP
Project ID
Project Name | Online Banking Form
Prepared/Modified by | Role | Date of Preparation
Bug Squashers | Tester | 2018-07-23
Reviewed by | Role | Date of Review
Swathi | Test Lead
Approved by | Role | Date of Approval
Geethika | Test Manager
Circulation List
Version Number | 1

## DEFECT TRACKING SHEET
Project ID: Prj_OnlineBanking_01 |  | Project Name : ONLINE BANKING SYSTEM
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Fixed By | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments
OBS_001 | password | The invalid user id and password are entered more than 3 times the account will not be locked | Detailed Description: The invalid username and password are entered more than 3 times Steps to reproduce a bug: 1. Open Browser 2. Enter URL for the website 3. Enter the admin details 4. Enter the invalid username and password more than 3 times. 5. Click on Login button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the account is not blocked when invalid details is given more than 3 times. | Coding | Internet Explorer | Internal Dev | Medium | High | 1.1 | Build 1.0 | 2018-07-19 | bhavya |  | ACT | Test Cycle 1 | TC_AdminPass_06
OBS_002 | Acc_Hold_addr | The account holder address in the registration page it is accepting single character also | Detailed Description: The holder address in the registration form is accepting single character Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on admin details 4. Enter the Valid credentials 5. Click on Login button 6.The website should generate Account Holder Registration page. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the account holder address is accepting single character also. | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2018-07-19 | bhavya |  |  | Test Cycle 1 | TC_Addr_03
OBS_003 | Register | The account holder is able to register by clicking register button if fields are not entered | Detailed Description: The holder is able to register if fileds are not entered Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on admin details 4. Enter the Valid credentials 5. Click on Login button 6.The website should generate Account Holder Registration page. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the account holder is able to register if fileds are not entered properly | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2018-07-19 | bhavya |  |  | Test Cycle 1 | TC_Reg_02
OBS_004 | Reset | The account holder is not able to reset by clicking reset button | Detailed Description: The holder is not able to reset the reset button Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on admin details 4. Enter the Valid credentials 5. Click on Login button 6.The website should generate Account Holder Registration page. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the account holder is not able to reset the fields | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2018-07-19 | bhavya |  |  | Test Cycle 1 | TC_Res_02
OBS_005 | multiple_accounts | The Mini/Detailed statements are not present in account holder page | Detailed Description: The holder is not able to view mini/detailed statements Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on admin details 4. Enter the Valid credentials 5. Click on Login button 6.The website should generate Account Holder Registration page. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the account holder is not able to view the mini/detailed accounts(multiple accounts) they are not present in account holder page. | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2018-07-19 | bhavya |  |  | Test Cycle 1
OBS_006 | request_change | The request for change in communication address/mobile number for bank account is not present | Detailed Description: The holder is not able to change mobile number/address Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on admin details 4. Enter the Valid credentials 5. Click on Login button 6.The website should generate Account Holder Registration page. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the account holder is not able to change in communication address/mobile number in account holder page. | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2018-07-19 | bhavya |  |  | Test Cycle 1
OBS_007 | fund_transfer | The fund transfer for bank accounts by clicking 'Add a payee' button is not provided in page | Detailed Description: The holder is not able to transfer funds into bank accounts Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on admin details 4. Enter the Valid credentials 5. Click on Login button 6.The website should generate Account Holder Registration page. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the account holder is not able to transfer the funds into another account. | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2018-07-19 | bhavya |  |  | Test Cycle 1
OBS_008 | payments | The transactions is not completed successfully if pay button is not provided in page | Detailed Description: The holder is not able to complete transactions successfully Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on admin details 4. Enter the Valid credentials 5. Click on Login button 6.The website should generate Account Holder Registration page. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the account holder is not able to do transactions successfully if pay button is not provided | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2018-07-19 | bhavya |  |  | Test Cycle 1
OBS_009 | pan_card | The registration page is showning the pan card is already existing for every new account | Detailed Description: The holder page is showing the pan card is already existing Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on admin details 4. Enter the Valid credentials 5. Click on Login button 6.The website should generate Account Holder Registration page. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the account holder page is showing the pan card is already existing. | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2018-07-19 | bhavya |  |  | Test Cycle 1 | Tc_Pc_07
OBS_010 | Email_Id | The registration page is showning the Email Id is already existing for every new account | Detailed Description: The holder page is showing the Email Id is already existing Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on admin details 4. Enter the Valid credentials 5. Click on Login button 6.The website should generate Account Holder Registration page. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the account holder page is showing the Email Id is already existing. | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2018-07-19 | bhavya |  |  | Test Cycle 1 | Tc_Eml_03
OBS_011 | pan_card | The pan card is accepting any pattern | Detailed Description: The holder page is showing the pan card is accepting any pattern Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on admin details 4. Enter the Valid credentials 5. Click on Login button 6.The website should generate Account Holder Registration page. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the account holder page is showing the pan card is validating when wrong pattern is given. | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2018-07-19 | bhavya |  |  | Test Cycle 1 | Tc_Pc_03
OBS_012 | Acc_Hold_Name | The account holder name in the registration page it accepting numerical characters | Detailed Description: The holder name in the registration form is accepting numerical characters Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on admin details 4. Enter the Valid credentials 5. Click on Login button 6.The website should generate Account Holder Registration page. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the account holder name is accepting numerical characters. | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2018-07-19 | bhavya |  |  | Test Cycle 1 | TC_AcHName_03
OBS_013 | secret_answer | It validates the secret answer when secret question is left with blank. | Detailed Description: The secret answer is accepting when the question is left with blank Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on admin details 4. Enter the Valid credentials 5. Click on Login button 6.The website should generate Account Holder Registration page. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the secret answer is accepting when question is left with blank. | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2018-07-19 | bhavya |  |  | Test Cycle 1 | TC_SA_02